## Introduction
Project name - Testing E-Commerce Web Application
Sr. no | Document name | Testing type | Team Member | Testing module | No of Bugs | Status | Remark
1 | Defect Report | Manual testing | Jaikrishnaa SA Jhanavi K Vinod Kumar Keshav Baradwaj Sai Pranathi | Registration | 16 | New
2 |  |  |  | Login | 2 | New
3 |  |  |  | Contact us | 6 | New
4 |  |  |  | Subscription | 1 | New
5 |  |  |  | Products | 2 | New
|  |  |  | Total | 27

## Bug_report_REG
Defect Report For Regstration Page
S.No | Defect ID | Title/Summary | Description | Module/Feature | Priority | Serverity | Environment | Steps to reproduce | Expected Result | Actual Result | Reported by | Reported date | Assigned to | Status | Retest date | Remark
1 | Bug_Reg01 | Input issue in name field | To verify and validate the signup up feature with valid name and invalid email in signup/login page. | Registration | High | Medium | SIT | Step1: Open the url Step 2: Enter valid name and invalid email Step 3: Click on signup button Step 4: Analyze the result | User should not be able to register/ redirect to the registration page | User is able to register / redirect to registartion page | Jaikrishnaa SA | 13/08/2025 | Developer 1 | New
2 | Bug_Reg02 | Input issue in name field with invalid name and email field with invalid email | To verify and validate the signup up feature with invalid name and valid email in signup/login page. | Registration | High | Medium | SIT | Step1: Open the url Step 2: Enter invalid name and valid email Step 3: Click on signupbutton Step 4: Analyze the result | User should not be able to register/ redirect to the registration page | User is able to register / redirect to registartion page | Jaikrishnaa SA | 13/08/2025 | Developer 1 | New
3 | Bug_Reg03 | Input issue in name field with invalid name and email field with invalid email | To verify and validate the signup up feature with invalid name and invalid email in signup/login page. | Registration | High | Medium | SIT | Step1: Open the url Step 2: Enter invalid name and invalid email Step 3: Click on signupbutton Step 4: Analyze the result | User should not be able to register/ redirect to the registration page | User is able to register / redirect to registartion page | Jaikrishnaa SA | 13/08/2025 | Developer 1 | New
4 | Bug_Reg04 | Input issue in name field | To verify and validate the text box (Name) with invalid name in the signup page | Registration | High | Medium | SIT | Step1: Open the url Step 2: Click on signup button with valid credential Step 3: Validate the text box (Name) with invalid name Step 4: Analyze the result | User should not be able to register. Message pops up with invalid Name | User is able to register / redirect to registartion page with invalid name | Jaikrishnaa SA | 13/08/2025 | Developer 1 | New
5 | Bug_Reg05 | Input issue in password field | To verify and validate the text box (password) with invalid password in the signup page | Registration | High | Medium | SIT | Step1: Open the url Step 2: Click on signup button with valid credential Step 3: Validate the text box (Password) with invalid Password Step 4: Analyze the result | User should not be able to register. | User is able to register | Jaikrishnaa SA | 13/08/2025 | Developer 1 | New
6 | Bug_Reg06 | Input issue in date field | To verify and validate the date with month in the signup page | Registration | High | Medium | SIT | Step1: Open the url Step 2: Click on signup button with valid credential Step 3: Validate the dates with corresponding months. Step 4: Analyze the result | User should be able to select valid date corresponding to the months only. | User is able to choose wrong date and register example(feb 21) | Jaikrishnaa SA | 13/08/2025 | Developer 1 | New
7 | Bug_Reg07 | Input issue in First name field | To verify and validate the text box (First Name) with invalid name in the signup page | Registration | High | Medium | SIT | Step1: Open the url Step 2: Click on signup button with valid credential Step 3: Validate the text box (First Name) with invalid name Step 4: Analyze the result | User should not be able to register. | User is able register with in invalid first name | Jaikrishnaa SA | 13/08/2025 | Developer 1 | New
8 | Bug_Reg08 | Input issue in Last name field | To verify and validate the text box (Last Name) with invalid name in the signup page | Registration | High | Medium | SIT | Step1: Open the url Step 2: Click on signup button with valid credential Step 3: Validate the text box (Last Name) with invalid name Step 4: Analyze the result | User should not be able to register. | User is able register with in invalid Last Name | Jaikrishnaa SA | 13/08/2025 | Developer 1 | New
9 | Bug_Reg09 | Input issue in Company name field | To verify and validate the text box (Company Name) with invalid name in the signup page | Registration | High | Medium | SIT | Step1: Open the url Step 2: Click on signup button with valid credential Step 3: Validate the text box (Company Name) with invalid name Step 4: Analyze the result | User should not be able to register. | User is able register with in invalid Company Name | Jaikrishnaa SA | 13/08/2025 | Developer 1 | New
10 | Bug_Reg10 | Input issue in Address field | To verify and validate the text box (Address) with invalid name in the signup page | Registration | High | Medium | SIT | Step1: Open the url Step 2: Click on signup button with valid credential Step 3: Validate the text box (Address) with invalid name Step 4: Analyze the result | User should not be able to register. | User is able register with in invalid Address | Jaikrishnaa SA | 13/08/2025 | Developer 1 | New
11 | Bug_Reg11 | Input issue in Address2 field | To verify and validate the text box (Address2) with invalid name in the signup page | Registration | High | Medium | SIT | Step1: Open the url Step 2: Click on signup button with valid credential Step 3: Validate the text box (Address2) with invalid name Step 4: Analyze the result | User should not be able to register. | User is able register with in invalid Address2 | Jaikrishnaa SA | 13/08/2025 | Developer 1 | New
12 | Bug_Reg12 | Input issue in State name field | To verify and validate the text box (State Name) with invalid name in the signup page | Registration | High | Medium | SIT | Step1: Open the url Step 2: Click on signup button with valid credential Step 3: Validate the text box (State Name) with invalid name Step 4: Analyze the result | User should not be able to register. | User is able register with in invalid State Name | Jaikrishnaa SA | 13/08/2025 | Developer 1 | New
13 | Bug_Reg13 | Input issue in City name field | To verify and validate the text box (City Name) with invalid name in the signup page | Registration | High | Medium | SIT | Step1: Open the url Step 2: Click on signup button with valid credential Step 3: Validate the text box (City Name) with invalid name Step 4: Analyze the result | User should not be able to register. | User is able register with in invalid City Name | Jaikrishnaa SA | 13/08/2025 | Developer 1 | New
14 | Bug_Reg14 | Input issue in Zipcode field | To verify and validate the text box (Zipcode) with invalid name in the signup page | Registration | High | Medium | SIT | Step1: Open the url Step 2: Click on signup button with valid credential Step 3: Validate the text box (Zipcode) with invalid name Step 4: Analyze the result | User should not be able to register. | User is able register with in invalid Zipcode | Jaikrishnaa SA | 13/08/2025 | Developer 1 | New
15 | Bug_Reg15 | Input issue in password field | To verify and validate the show password (eye) button | Registration | High | Medium | SIT | Step1: Open the url Step 2: Click on signup button with credentials Step 3: After typing password click on sow password Step 4: Analyze the result | User should be able to view password after typing | User is unable to click on show password after viewed once | Jaikrishnaa SA | 13/08/2026 | Developer 2 | New
16 | Bug_Reg16 | Input issue in mobile number field | To verify and validate the text box (Mobile number) with invalid name in the signup page | Registration | High | Medium | SIT | Step1: Open the url Step 2: Click on signup button with valid credential Step 3: Validate the text box (Mobile number) with invalid name Step 4: Analyze the result | User should not be able to register. | User is able register with in invalid Mobile number | Jaikrishnaa SA | 13/08/2026 | Developer 2 | New

## Bug_report_login
Defect Report For Regstration Page
S.No | Defect ID | Title/Summary | Description | Module/Feature | Priority | Serverity | Environment | Steps to reproduce | Expected Result | Actual Result | Reported by | Reported date | Assigned to | Status | Retest date | Remark
1 | Bug_login_1 | Issue in the login feid with unregistered email | To verify and validate the login feature with non registered mail id | Login | Medium | High | SIT | Step1: Open the url Step 2: Enter unregistered mail id Step 3: Click on login button Step 4: Analyze the result | User should not be able to login. Message pops up with Mail id not found | Message pops up with wrong mail ID | Jaikrishnaa SA | 13/08/2025 | Developer 1 | New
2 | Bug_login_2 | Issue in the password field in the show password (eye) button | To verify and validate the show password (eye) button in password field of login | Login | Medium | High | SIT | Step1: Open the url Step 2: Enter unregistered mail id Step 3: Click on eye button after entering the password Step 4: Analyze the result | User should be ableclick and eye button and view password | Eye button is not available after used once | Jaikrishnaa SA | 13/08/2025 | Developer 1 | New

## Bug_report_contactus
Defect Report For Contact us Page
S.No | Defect ID | Title/Summary | Description | Module/Feature | Priority | Serverity | Environment | Steps to reproduce | Expected Result | Actual Result | Reported by | Reported date | Assigned to | Status | Retest date | Remark
1 | Bug_Contact01 | Issue in the name field | To verify and validate the InValid Name in Name Text box in contact us page | Contact us | Medium | Medium | SIT | step 1 : Open any browser - Chrome , Firefox step 2 : Type the URL step 3 : Type InValid Name in Name text box | User Should not able to submit | User is able to submit with invalid name | Jaikrishnaa SA | 13/08/2025 | Developer 1 | New
2 | Bug_Contact02 | Issue in the name field with no input | To verify and validate the no Name in Name Text box in contact us page | Contact us | Medium | Medium | SIT | step 1 : Open any browser - Chrome , Firefox step 2 : Type the URL step 3 : Type no Name in Name text box | User Should not able to submit | User is able to submit with no name | Jaikrishnaa SA | 13/08/2025 | Developer 1 | New
3 | Bug_Contact03 | Issue in the email field | To verify and validate the InValid email in email Text box in contact us page | Contact us | Medium | Medium | SIT | step 1 : Open any browser - Chrome , Firefox step 2 : Type the URL step 3 : Type InValid email address in email text box | User Should not able to submit | User is able to submit with invalid email | Jaikrishnaa SA | 13/08/2025 | Developer 1 | New
4 | Bug_Contact04 | Issue in the email field | To verify and validate the no email in email Text box in contact us page | Contact us | Medium | Medium | SIT | step 1 : Open any browser - Chrome , Firefox step 2 : Type the URL step 3 : Type no email address in email text box | User Should not able to submit | User is able to submit with no email | Jaikrishnaa SA | 13/08/2025 | Developer 1 | New
5 | Bug_Contact05 | Issue in the subject field | To verify and validate the Subject Text box with no input in contact us page | Contact us | Medium | Medium | SIT | step 1 : Open any browser - Chrome , Firefox step 2 : Type the URL step 3 : Enter in Subject text box with no input | User Should not able to submit | User is able to submit with no subject | Jaikrishnaa SA | 13/08/2025 | Developer 1 | New
6 | Bug_Contact06 | Issue in the message field | To verify and validate the Your message Here Text box with no input in contact us page | Contact us | Medium | Medium | SIT | step 1 : Open any browser - Chrome , Firefox step 2 : Type the URL step 3 : Enter in Your message Here Text box with no input | User Should not able to submit | User is able to submit without message | Jaikrishnaa SA | 13/08/2025 | Developer 1 | New

## Bug_report_Subscription
Defect Report For Regstration Page
S.No | Defect ID | Title/Summary | Description | Module/Feature | Priority | Serverity | Environment | Steps to reproduce | Expected Result | Actual Result | Reported by | Reported date | Assigned to | Status | Retest date | Remark
1 | Bug_subsc_1 | Issue in the subscription part in | To verify and validate the textbox (Email) in subscription in home page with invalid Email | Subscription | Medium | High | SIT | Step1: Open the url Step 2: Check wheather the textbox(Email) is accepts invalid Step 3: Analyze the result | User should not be able to enable subscribefor their account | Working with invalid mail | Jaikrishnaa SA | 13/08/2025 | Developer 1 | New

## Bug_report_Products
Defect Report For Regstration Page
S.No | Defect ID | Title/Summary | Description | Module/Feature | Priority | Serverity | Environment | Steps to reproduce | Expected Result | Actual Result | Reported by | Reported date | Assigned to | Status | Retest date | Remark
1 | Bug_product_1 | Issue in the name feid with in invalid name in review | To verify and validate the name with invalid input in the product page | Product | Medium | High | SIT | step 1 : Open any browser - Chrome , Firefox step 2 : Type the URL step 3 : Enter name with invalid input in product page | User Should not able to enter invalid input in name | User is able to submit with invalid name | Jaikrishnaa SA | 13/08/2025 | Developer 1 | New
2 | Bug_product_2 | Issue in the email feid with in invalid email in review | To verify and validate the email with invalid input in the product page | Product | Medium | High | SIT | step 1 : Open any browser - Chrome , Firefox step 2 : Type the URL step 3 : Enter email with invalid input in product page | User Should not able to enter invalid input in email | User is able to submit with invalid email | Jaikrishnaa SA | 13/08/2025 | Developer 1 | New

## Sheet1
Defect Report For Regstration Page
S.No | Defect ID | Title/Summary | Description | Module/Feature | Priority | Serverity | Environment | Steps to reproduce | Expected Result | Actual Result | Reported by | Reported date | Assigned to | Status | Retest date | Remark
1 | Bug_001 | Input issue in mobile number field | To verify and validate the text box (Mobile number) with invalid name in the signup page | Registration | High | Medium | SIT | Step1: Open the url Step 2: Click on signup button with valid credential Step 3: Validate the text box (Mobile number) with invalid name Step 4: Analyze the result | User should not be able to register. | User is able register with in invalid Mobile number | Jaikrishnaa SA | 13/08/2026 | Developer 2 | New
2 | BUG_002 | Issue in the name feid with in invalid name in review | To verify and validate the name with invalid input in the product page | Product | Medium | High | SIT | step 1 : Open any browser - Chrome , Firefox step 2 : Type the URL step 3 : Enter name with invalid input in product page | User Should not able to enter invalid input in name | User is able to submit with invalid name | Jaikrishnaa SA | 13/08/2025 | Developer 1 | New
3 | BUG_003 | Issue in the email feid with in invalid email in review | To verify and validate the email with invalid input in the product page | Product | Medium | High | SIT | step 1 : Open any browser - Chrome , Firefox step 2 : Type the URL step 3 : Enter email with invalid input in product page | User Should not able to enter invalid input in email | User is able to submit with invalid email | Jaikrishnaa SA | 13/08/2025 | Developer 1 | New